## Sheet1
Risk No. | Risk item | Effect | Cause | Probability | Severity | Actions to Minimize Risks | Final review
Project Planning
1.1.1 | Setting unrealistic deadlines and milestones | Poor planning and authorisation with clients can damage relationship with clients AND team members. This will also have effects on some of the development as features and architechure will no be properly researched and designed. effects, from 'bricked' devices to software issues | Poor planning and communication between parties unusable devices | 2 | 4 | provide realisitic deadlines to clients, plan ahead allowing more time to develop, issue yourself enough time to complete your tasks.
1.1.2 | Agreeing unrealistic targets | Prioritising features that are either unobtainable or unnecessary can not only effect the quality of the end product, but also showcases poor management of product expectations and can effect internal relations with clients | Promising features that are otherwise unachieveble. | 2 | 4 | be realistic with the features and functionality of your project, set up transparent communication channels with clients/developers, manage expectations and emotions of your clients in reference to their experience and knowledge of the projects themes.
1.1.3 | Poor judgement of ability | inability to complete tasks due to lack of knowledge can strongly impact the quality and the chance of deliverance of the project. This can also result in a poor relationship with management/clients and will most likely result in expulsion from the project and course. | Little Commitment to learning material, Poor training from trainers, Little practice of methodologies. | 1 | 4 | Arrive on time to every training period, apply self to provided training materials, practice taught materials in personal time. Assign targets according to your own ability, engage with trainers and collegues on issues
1.1.4 | Change in project specification | depending on the lateness of a change, as well as the serious of said change, this will massive effect the project from all aspects from architecture, to methodologies used. Whilst this usually will be agreed with the client/management, | Change in requirements from internal/external sources. | 1* | 1* | plan ahead for extra time to complete said changes. Priortise particular features and parts that may be less vunerable for change. Organise a deadline extenision for the project.
Project Development
1.2.1 | Poor accessibility to appropriate software/ hardware | Poor or no access to related hardware and/or software can effect both the accessibility of the project. files, as well as the progression towards expected milestones. | Limited access to sufficient machines, little to no cloud storage capability, downtime on related services and privacy concerns. | 2 | 3 | Provide access and resources to efficient hardware and software that allow developers to fufill their projects. Setup remote access to related platforms and documents.
1.2.2 | SQL Injection Attacks | Common hacking technique that can drastically change or destroy my database, resulting in inefficiency of project deliverables. Illegal access to database and its data. | neglegtion of code for database and input of malicious table entries and code. concerns | 2 | 5 | Use single quote characters and examine database for errors and anomalies, use parameterized queries instead of string concatenation.
1.2.3 | Phising Attack | Can result in lose of important confidential data regarding both your project AND company files. Breaches business security protocols, can result in expulsion | Accessing links from un-authorised email addresses, issuing login details to other accounts | 2 | 5 | Never store usernames, passwords on public devices, only access project. Lock PCs. Never click links from external contacts related systems from authorised terminals.
1.2.4 | DDoS/Network Attack | Downtime for either our internal network or the networks of the sites and services we use can result in little to no access to systems needed to progress project. Direct DDoS attacks can prevent internet access and may also reveal flaws of business networks, resulting in further attacks | Multiple systems flood the the bandwidth of a targetted system. Frequent for larger servie providers | 2 | 4 | Whilst most larger service providers will have these measures in place to protect from these attacks, businesses like ourselves can build redundancy into network infrastructure and deploy anti DDoS hardware and software modules to make it harder for attacks.
Health and Conditioning
1.3.1 | Possibility of illness | Falling ill during both the planning and development phases of the projec can result in a loss of time, as well as a drop in quality for the project | Poor Hygiene, poor diet, stress | 1 | 2 | Continue with basic hygiene routine, eat/drink enough, take frequent breaks, use prescribed medicines if applicable, provide enough time to catch up with work.
1.3.2 | Eye Strain | Eye strain can have potential effects on the quality of work produced, and could effect the chance of meeting deadlines for deliverables | Heavy Screen time, not taking frequent breaks from computer | 1 | 1 | Abide and respect breaks issued by QA.
1.3.3 | Posture/Ergonomics related issues | issues regarding posture and lack of ergonic support can not only affect the long term health of a developer, it can also affect the standard of work produced due to the undesireale conditions of the developer. | Heavy Screen time, not taking frequent breaks from computer | 1 | 2 | Provide developer(s) with suitable ergonic support such as workchairs, wrist supports ect.. Abide and respect breaks issued by QA.
1.3.4 | Distruption due to current world events | Depending on the serverity of measures put in place by either the client(QA) or the government, some of the other issues stated prior could be escaled to high severity. Likely risks include illness, isolation, little access to work content and even possible closure of project. | Spread of COVID-19 | 5 | 5 | Ensure that has been protocols made to ensure productivity at home or at remote locations. Establish remote communication links and potentially adjust the goals and targets to match the severity of the current scenario.
*: both Probability and Severity of this issue will depend on notice period compared to original deadline
*: severity and probabiity of most the items lists may be affected by the COVID-19 Outbreak (16/03/20)
Key: Likelihood and Impact Scale uses a 1-5 scale, with 1 being not very strong and 5 being very strong